## Checklist for success
Microsoft 365 Copilot for SMB
Checklist for success
Utilize this checklist to begin your implementation process. Import into Microsoft Lists or add additional content as needed in your organization.
Task ID | Task | Description | Status | Assigned To | Due Date | Start Date | End Date
1 | Identify your succes team. Nominate and activate your Copilot executive sponsors. | As part of your essentials for Copilot success, identify a user enablement specialist/user experience staff, IT technical staff, executives and other stakeholders for the core team. Align on the AI to business strategy with the best practice of hosting an AI council or steering committee. | Not Started
2 | Address and assess technical readiness. | Understand and address data security, governance and data access questions. | Not Started
3 | Design user experience strategy, including end user support and readiness communications plan. | Fill out your AI transformation roadmap (slide 19 in the Copilot SMB Implementation Guide) to build your shared Copilot implementation scenarios dating from quick wins to your yearly goal. | Not Started
4 | Design your path to secure your data for compliance and peace of mind. | Prepare tenant for healthy deployment per Microsoft recommendations. | Not Started
5 | Be intentional with assignments and concentrate seats. Define initial high value scenarios and target a critial mass of users for rapid value. | Select early adopters, aka Flight Crew team. Select employees who will use new capabilities and share feedback. | Not Started
6 | Ensure appropriate Data Security controls are in place. | Review slide 8 of the Copilot SMB Implementation Guide. If needed, deploy additional Microsoft 365 apps. | Not Started
7 | Use the new Microsoft 365 Copilot set up guide. | Find this wizard in the admin center > Home > Setup page > Apps and Email > Get ready for Microsoft 365 Copilot (https://setup.cloud.microsoft/copilot-for-microsoft-365/setup-guide). | Not Started
8 | Deploy training, Champion programs, an engagement community and standardize ongoing training. | Onboard and train a peer to peer Champion team to provide support and guidance during end user onboarding and initial usage of Copilot features. Provide onboarding materials and check in regularly. Schedule office hours for support and prompt sharing. Best practices: Prompt gallery, onboarding email templates and community of practice. | Not Started
9 | Use the Copilot Dashboard to reveal user engagement activity. | Review the Copilot Dashboard to review admin useage reports, analyze user retention and engagement. Leverage this User Survey Kit (https://aka.ms/CopilotUserSurvey) to keep a pulse on how Copilot is impacting your users’ day-to-day and gather sentiment and impact learnings. | Not Started
10 | Qualify impact and build momentum. | Qualify growth, cost savings and employee benefits. Build momentum with success stories and knowledge sharing. Best practices: Scenario library, use case materials and planning worksheet. | Not Started
11 | Create unique experiences. | Design, build and publish plug-ins to deliver unique experiences. Build your own Copilots. | Not Started

## Values (hidden)
Status
Not Started
In Progress
Pending Info
Blocked
Completed
Deferred